## Test Cases
Project Name: [PRD]Hilton Intutive Survey Environment: https://botstg.bonp.me/ BID: 1638 QR Code: TBD Flow: フロー Figma: Figma Design Documentation: [PRD]Hilton Intutive Survey | [9 empty] | Results
# | CASE# | SCENARIO | PRE-REQUISITES | CASE DESCRIPTION | REPRODUCTION STEPS | EXPECTED RESULTS | REFERENCE | TESTER 1 | TESTER 2 | RESULT TESTER 1 | RESULT TESTER 2 | COMMENTS
1 | 1.1 | Accessing the bot | - | Verify the user is able to access the bot by scanning the QR code | Scan the QR code | The user is able to access the LINE bot chat by scanning the QR ocde and add the bot as a friend |  | @Galyna Slobodyanyk | @Khrystyna Chuchman | Pass | SKIP
| 1.2 | Friend check | Not having the bot as a friend | Verify that the bot can be added a friend without issue |  | The bot can be added a friend without issue |  | @Galyna Slobodyanyk | @Khrystyna Chuchman | Pass | SKIP
2 | 2.1 | Event period (XX〜XXの期間)?? | Event outside of time period | Verify that the bot can be accessed within the event period | Tapping the push notification | The LP screen displayed matches the design |  | @Galyna Slobodyanyk | @Khrystyna Chuchman | Pass | Pass
| 2.2 |  |  |  | Tapping the rich menu |  |  | @Galyna Slobodyanyk |  | Pass | Pass
| 2.3 |  | Event outside of time period/Timezone differences |  | Tapping the rich menu |  |  | @Galyna Slobodyanyk |  | Pass | Pass
| 2.4 |  | Event within time period | Verify that the bot cannot be access outside the event period | Tapping the push notification | The period expired screen displayed matches the design |  | @Galyna Slobodyanyk | @Khrystyna Chuchman | SKIP | SKIP
| 2.5 |  |  |  | Tapping the rich menu |  |  | @Galyna Slobodyanyk |  | SKIP | SKIP
| 2.6 |  | Event within time period/Timezone differences |  | Tapping the rich menu |  |  | @Galyna Slobodyanyk |  | SKIP | SKIP
3 | 3.1 | LP screen | - | Verify that the LP screen is free of visual and functional defects | Access LP page | No visual or functional issues are present on the LP page |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 3.2 |  | - | Verify that the link is functional | 1. Access LP page 2. Click on "利用規約" and "プライバシーポリシー" link | Pressing the link brings you to the correct screen ・プライバシーポリシーの遷移先 https://line.me/R/app/1657073247-Dxg49yBR?type=app&b=4669&v=83956&_platform=line ・利用規約の遷移先 https://line.me/R/app/1657073247-Dxg49yBR?type=app&b=4669&v=83958&_platform=line |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 3.3 |  | - | Verify that the checkbox is required | 1. Access LP page 2. Confirm the "診断をはじめる" button without check the checkbox | "診断をはじめる" button is disable |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 3.4 |  | - |  | 3. Check./Uncheck the checkbox | "診断をはじめる" button is enable/disable based on the check |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 3.5 |  | - |  | 3. Check the checkbox and press the "診断をはじめる" button | Pressing the "診断をはじめる" button brings you to the 診断済み判定 |  | @Galyna Slobodyanyk |  | SKIP | SKIP
| 3.6 |  | 未診断 | Verify 診断済み判定 | 3. Check the checkbox and press the "診断をはじめる" button | Bring you to 質問１ screen |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 3.7 |  | 診断済 |  | 3. Check the checkbox and press the "診断をはじめる" button | Bring you to 診断結果 screen |  | @Galyna Slobodyanyk |  | SKIP | SKIP
4 | 4.1 | 質問１ screen | - | Verify that the 質問１ screen is free of visual and functional defects | 1. Access 質問１ page | No visual or functional issues are present on the 質問１ page - correct question text and answer choices - single-select behavior |  | @Galyna Slobodyanyk |  | Pass | Not tested
| 4.1.1 |  | - |  | 2. Tab the answer | No question is skipped in the normal forward flow: Q1 → Q2 after tab the answer |  | @Galyna Slobodyanyk |  | Pass | Not tested
| 4.2 | 質問２ screen | - | Verify that the 質問２ screen is free of visual and functional defects | 1. Answer 質問１ and redirected to 質問２ | No visual or functional issues are present on the 質問２ page - correct question text and answer choices |  | @Galyna Slobodyanyk |  | Pass | Not tested
| 4.2.1 |  | - |  | 2. Tab the answer | No question is skipped in the normal forward flow: Q2 → Q3 after tab the answer |  | @Galyna Slobodyanyk |  | Pass | Not tested
| 4.3 | 質問３ screen | - | Verify that the 質問３ screen is free of visual and functional defects | 1. Answer 質問２ and redirected to 質問３ | No visual or functional issues are present on the 質問３ page - correct question text and answer choices |  | @Galyna Slobodyanyk |  | Pass | Not tested
| 4.3.1 |  | - |  | 2. Tab the answer | No question is skipped in the normal forward flow: Q3 → Q4 after tab the answer |  | @Galyna Slobodyanyk |  | Pass | Not tested
| 4.4 | 質問４ screen | - | Verify that the 質問４ screen is free of visual and functional defects | 1. Answer 質問３ and redirected to 質問４ | No visual or functional issues are present on the 質問４ page - correct question text and answer choices |  | @Galyna Slobodyanyk |  | Pass | Not tested
| 4.4.1 |  | - |  | 2. Tab the answer | No question is skipped in the normal forward flow: Q4 → Q5 after tab the answer |  | @Galyna Slobodyanyk |  | Pass | Not tested
| 4.5 | 質問５ screen | - | Verify that the 質問５ screen is free of visual and functional defects | 1. Answer 質問４ and redirected to 質問５ | No visual or functional issues are present on the 質問５ page - correct question text and answer choices |  | @Galyna Slobodyanyk |  | Pass | Not tested
| 4.5.1 |  | - |  | 2. Tab the answer | Tab the answer brings you to the loading screen |  | @Galyna Slobodyanyk |  | Pass | Not tested
5 | 5.1 | Loading screen | - | Verify that the Loading screen is free of visual and functional defects | Complete the survey and redirected to Loading screen | The loading screen is displayed immediately after Q5 is answered |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 5.2 |  | - |  |  | The CSS animation plays correctly (not a GIF) without flickering or freezing |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 5.3 |  | - |  |  | The animation is displayed correctly on both iOS and Android |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 5.4 |  | - |  | Loading complete | After the defined fixed duration, the user is automatically redirected to the result branching screen |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
6 | 6.1 | 診断結果 screen (Pattern 1) Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1556656707#gid=1556656707 | - | Verify that the 診断結果 screen (Pattern 1) is free of visual and functional defects | Access 診断結果 screen (Pattern 1) | No visual or functional issues are present on the screen - The correct result type name, description, and recommended content are shown for each of the 4 patterns. - Recommended hotels (おすすめホテル) area - 詳細を見る button - Hiltonホテルの一覧を見る button - 診断タイプ一覧 button - 診断結果をシェアする button - Xでシェアする button - もう一度診断する link |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 6.2 |  | - | Verify that the button and link is functional | Press the 詳細を見る button | ?? マスターデータで登録したおすすめのホテルステイのURLを開く |  | @Galyna Slobodyanyk | @Tina | Pass | Pass
| 6.3 |  | - |  | Press the Hiltonホテルの一覧を見る button | Redirect to https://www.hilton.com/ja/locations/japan/?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-Hotel_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 6.4 |  | - |  | Press the 診断タイプ一覧 button | Pressing the "診断タイプ一覧" button brings you to the 診断タイプ一覧 - Press the 戻る button brings you to the 診断結果 screen (Pattern 1) |  | @Galyna Slobodyanyk |  | Pass | Fail | bug id 4
| 6.5 |  | - |  | Press the ヒルトン・オナーズに新規登録 | Redirect to https://portal.asiapac.hilton.com/ja/join?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-HiltonHonorsNew_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 6.6 |  | - |  | Press the LINEでヒルトン・オナーズにログイン | Redirect to https://www.hilton.com/ja/hilton-honors/login/?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-HiltonHonorslogin_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 6.7 |  | - |  | Press the 診断結果をシェアする button | Pressing the "診断結果をシェアする" button シェアターゲットピッカー display - Able to share via LINE - The share message is sent as a Rich Message (text + image) as specified Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1908178035#gid=1908178035 |  | @Galyna Slobodyanyk |  | Pass | Fail | bug id 5
| 6.8 |  | - |  | Pres the Xでシェアする button | Pressing the "Xでシェアする" button redirect to X - Able to share via X - The share message is sent as a Rich Message (text + image) as specified Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1908178035#gid=1908178035 |  | @Galyna Slobodyanyk |  | Pass | Fail | bug id 6
| 6.9 |  | - |  | Press the もう一度診断する link | Pressing the "もう一度診断する" button brings you to the LP page |  | @Galyna Slobodyanyk |  | Pass | Pass
| 6.10. |  | - | Verify that the push notification sent after survey is complete イマーシブ・リラックス型 | Complete survey with Pattern1 result | A push notification is sent immediately after survey completion - Off-peak notic? |  | @Galyna Slobodyanyk |  | SKIP | SKIP
7 | 7.1 | 診断結果 screen (Pattern 2) Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1556656707#gid=1556656707 | - | Verify that the 診断結果 screen (Pattern 2) is free of visual and functional defects | Access 診断結果 screen (Pattern 2) | No visual or functional issues are present on the screen - The correct result type name, description, and recommended content are shown for each of the 4 patterns. - Recommended hotels (おすすめホテル) area - 詳細を見る button - Hiltonホテルの一覧を見る button - 診断タイプ一覧 button - 診断結果をシェアする button - Xでシェアする button - もう一度診断する link |  | @Galyna Slobodyanyk |  | Pass | Pass
| 7.2 |  | - | Verify that the button and link is functional | Press the 詳細を見る button | ?? マスターデータで登録したおすすめのホテルステイのURLを開く |  | @Galyna Slobodyanyk |  | Pass | Pass
| 7.3 |  | - |  | Press the Hiltonホテルの一覧を見る button | Redirect to https://www.hilton.com/ja/locations/japan/?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-Hotel_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 7.4 |  | - |  | Press the 診断タイプ一覧 button | Pressing the "診断タイプ一覧" button brings you to the 診断タイプ一覧 - Press the 戻る button brings you to the 診断結果 screen (Pattern 2) |  | @Galyna Slobodyanyk |  | Pass | Pass
| 7.5 |  | - |  | Press the ヒルトン・オナーズに新規登録 | Redirect to https://portal.asiapac.hilton.com/ja/join?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-HiltonHonorsNew_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 7.6 |  | - |  | Press the LINEでヒルトン・オナーズにログイン | Redirect to https://www.hilton.com/ja/hilton-honors/login/?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-HiltonHonorslogin_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 7.7 |  | - |  | Press the 診断結果をシェアする button | Pressing the "診断結果をシェアする" button シェアターゲットピッカー display - Able to share via LINE - The share message is sent as a Rich Message (text + image) as specified Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1908178035#gid=1908178035 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 7.8 |  | - |  | Pres the Xでシェアする button | Pressing the "Xでシェアする" button redirect to X - Able to share via X - The share message is sent as a Rich Message (text + image) as specified Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1908178035#gid=1908178035 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 7.9 |  | - |  | Press the もう一度診断する link | Pressing the "もう一度診断する" button brings you to the LP page |  | @Galyna Slobodyanyk |  | Pass | Pass
| 7.10. |  | - | Verify that the push notification sent after survey is complete スマート・ステイ型 | Complete survey with Pattern2 result | A push notification is sent immediately after survey completion - Hilton Honors登録? |  | @Galyna Slobodyanyk |  | SKIP | SKIP
8 | 8.1 | 診断結果 screen (Pattern 3) Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1556656707#gid=1556656707 | - | Verify that the 診断結果 screen (Pattern 3) is free of visual and functional defects | Access 診断結果 screen (Pattern 3) | No visual or functional issues are present on the screen - The correct result type name, description, and recommended content are shown for each of the 4 patterns. - Recommended hotels (おすすめホテル) area - 詳細を見る button - Hiltonホテルの一覧を見る button - 診断タイプ一覧 button - 診断結果をシェアする button - Xでシェアする button - もう一度診断する link |  | @Galyna Slobodyanyk |  | Pass | Pass
| 8.2 |  | - | Verify that the button and link is functional | Press the 詳細を見る button | ?? マスターデータで登録したおすすめのホテルステイのURLを開く |  | @Galyna Slobodyanyk |  | Pass | Pass
| 8.3 |  | - |  | Press the Hiltonホテルの一覧を見る button | Redirect to https://www.hilton.com/ja/locations/japan/?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-Hotel_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 8.4 |  | - |  | Press the 診断タイプ一覧 button | Pressing the "診断タイプ一覧" button brings you to the 診断タイプ一覧 - Press the 戻る button brings you to the 診断結果 screen (Pattern 3) |  | @Galyna Slobodyanyk |  | Pass | Pass
| 8.5 |  |  |  | Press the ヒルトン・オナーズに新規登録 | Redirect to https://portal.asiapac.hilton.com/ja/join?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-HiltonHonorsNew_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 8.6 |  | - |  | Press the LINEでヒルトン・オナーズにログイン | Redirect to https://www.hilton.com/ja/hilton-honors/login/?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-HiltonHonorslogin_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 8.7 |  | - |  | Press the 診断結果をシェアする button | Pressing the "診断結果をシェアする" button シェアターゲットピッカー display - Able to share via LINE - The share message is sent as a Rich Message (text + image) as specified Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1908178035#gid=1908178035 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 8.8 |  | - |  | Pres the Xでシェアする button | Pressing the "Xでシェアする" button redirect to X - Able to share via X - The share message is sent as a Rich Message (text + image) as specified Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1908178035#gid=1908178035 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 8.9 |  | - |  | Press the もう一度診断する link | Pressing the "もう一度診断する" button brings you to the LP page |  | @Galyna Slobodyanyk |  | Pass | Pass
| 8.10. |  | - | Verify that the push notification sent after survey is complete ディープ・ホスピタリティ型 | Complete survey with Pattern3 result | A push notification is sent immediately after survey completion - アニバーサリー登録? |  | @Galyna Slobodyanyk |  | SKIP | SKIP
9 | 9.1 | 診断結果 screen (Pattern 4) Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1556656707#gid=1556656707 | - | Verify that the 診断結果 screen (Pattern 4) is free of visual and functional defects | Access 診断結果 screen (Pattern 4) | No visual or functional issues are present on the screen - The correct result type name, description, and recommended content are shown for each of the 4 patterns. - Recommended hotels (おすすめホテル) area - 詳細を見る button - Hiltonホテルの一覧を見る button - 診断タイプ一覧 button - 診断結果をシェアする button - Xでシェアする button - もう一度診断する link |  | @Galyna Slobodyanyk |  | Pass | Pass
| 9.2 |  | - | Verify that the button and link is functional | Press the 詳細を見る button | ?? マスターデータで登録したおすすめのホテルステイのURLを開く |  | @Galyna Slobodyanyk |  | Pass | Pass
| 9.3 |  | - |  | Press the Hiltonホテルの一覧を見る button | Redirect to https://www.hilton.com/ja/locations/japan/?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-Hotel_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 9.4 |  | - |  | Press the 診断タイプ一覧 button | Pressing the "診断タイプ一覧" button brings you to the 診断タイプ一覧 - Press the 戻る button brings you to the 診断結果 screen (Pattern 4) |  | @Galyna Slobodyanyk |  | Pass | Pass
| 9.5 |  | - |  | Press the ヒルトン・オナーズに新規登録 | Redirect to https://portal.asiapac.hilton.com/ja/join?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-HiltonHonorsNew_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 9.6 |  | - |  | Press the LINEでヒルトン・オナーズにログイン | Redirect to https://www.hilton.com/ja/hilton-honors/login/?WT.mc_id=zSREC0JP1MB2OLS3LINE4IntuitiveSurveyRevitalize-LIFF-HiltonHonorslogin_Apr5LIFF6MULTIBR7JA8&openExternalBrowser=1 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 9.7 |  | - |  | Press the 診断結果をシェアする button | Pressing the "診断結果をシェアする" button シェアターゲットピッカー display - Able to share via LINE - The share message is sent as a Rich Message (text + image) as specified Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1908178035#gid=1908178035 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 9.8 |  | - |  | Pres the Xでシェアする button | Pressing the "Xでシェアする" button redirect to X - Able to share via X - The share message is sent as a Rich Message (text + image) as specified Ref：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1908178035#gid=1908178035 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 9.9 |  | - |  | Press the もう一度診断する link | Pressing the "もう一度診断する" button brings you to the LP page |  | @Galyna Slobodyanyk |  | Pass | Pass
| 9.10. |  | - | Verify that the push notification sent after survey is complete セルフ・ディスカバリー型 | Complete survey with Pattern4 result | A push notification is sent immediately after survey completion - TBD |  | @Galyna Slobodyanyk |  | SKIP | SKIP
10 | 10.1 | 診断タイプ一覧 screen | - | Verify that the 診断タイプ一覧 screen is free of visual and functional defects | Pressing the "診断タイプ一覧" button on 診断結果 screen | No visual or functional issues are present on the screen - The correct content - 戻る button |  | @Galyna Slobodyanyk |  | Pass | Pass
11 | 11.1 | LP page 診断済み判定 | User done the survey with Pattern 1 | Verify that 診断済み判定 in LP page is functional | 1. Complete the survey with result Patter1 2. Access LP page 3. Press the 診断をはじめる button | Brings you to the 診断結果画面 イマーシブ・リラックス型 (Pattern 1) |  | @Galyna Slobodyanyk |  | Pass | Pass
| 11.2 |  |  |  | 4. Press the もう一度診断する link | Able to do and complete the survey again |  | @Galyna Slobodyanyk |  | Pass | Pass
| 11.3 |  | User done the survey with Pattern 2 | Verify that 診断済み判定 in LP page is functional | 1. Complete the survey with result Patter2 2. Access LP page 3. Press the 診断をはじめる button | Brings you to the 診断結果画面 スマート・ステイ型 (Pattern 2) |  | @Galyna Slobodyanyk |  | Pass | Pass
| 11.4 |  |  |  | 4. Press the もう一度診断する link | Able to do and complete the survey again |  | @Galyna Slobodyanyk |  | Pass | Pass
| 11.5 |  | User done the survey with Pattern 3 | Verify that 診断済み判定 in LP page is functional | 1. Complete the survey with result Patter3 2. Access LP page 3. Press the 診断をはじめる button | Brings you to the 診断結果画面 ディープ・ホスピタリティ型 (Pattern 3) |  | @Galyna Slobodyanyk |  | Pass | Pass
| 11.6 |  |  |  | 4. Press the もう一度診断する link | Able to do and complete the survey again |  | @Galyna Slobodyanyk |  | Pass | Pass
| 11.7 |  | User done the survey with Pattern 4 | Verify that 診断済み判定 in LP page is functional | 1. Complete the survey with result Patter4 2. Access LP page 3. Press the 診断をはじめる button | Brings you to the 診断結果画面 セルフ・ディスカバリー型 (Pattern 4) |  | @Galyna Slobodyanyk |  | Pass | Pass
| 11.8 |  |  |  | 4. Press the もう一度診断する link 5. Complete the survey again | Able to do and complete the survey again - push notification sent after survey is complete |  | @Galyna Slobodyanyk |  | Pass | Pass
12 | 12.1 | Edge cases | A user who started but did not complete the survey | Verify that 診断済み判定 in LP page is functional | 1. User started answer the question but not complete 2. Access LP page again 3. Press the 診断をはじめる button | Bring you to 質問１ screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 12.2 |  | A user who complete the survey once |  | 1. User complete the survey once 2. Press the 診断をはじめる button in LP page 3. Press the もう一度診断する link in result page 4. Do not complete the survey (close the app) 5. Open LP page and 診断をはじめる button again | Brings you to the 診断結果画面 (previously obtained Pattern results) |  | @Galyna Slobodyanyk |  | Pass | Pass
| 12.3 |  | A user who started but did not complete the survey |  | 1. Answer Q4 and close the app while loading screen display 2. Access LP page again 3. Press the 診断をはじめる button | Bring you to 質問１ screen |  | @Galyna Slobodyanyk |  | Pass | Pass
13 | 13.1.1 | 【正常系】 case 診断結果 navigation Ref: https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1084561786#gid=1084561786 | - | Each 診断 type should individually achieve the highest score and return the correct result. Type A 単独勝利 | Answer the survey as following Q1 : A Q2 : B Q3 : A Q4 : A Q5 : A | Type A イマーシブ・リラックス型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.1.2 |  | - | Type B 単独勝利 | Answer the survey as following Q1 : B Q2 : D Q3 : B Q4 : B Q5 : B | Type B スマート・ステイ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.1.3 |  | - | Type C 単独勝利（最高得点9点） | Answer the survey as following Q1 : C Q2 : C Q3 : C Q4 : C Q5 : C | Type C ディープ・ホスピタリティ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.1.4 |  | - | Type D 単独勝利 | Answer the survey as following Q1 : D Q2 : D Q3 : D Q4 : D Q5 : D | Type D セルフ・ディスカバリー型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.2.1 | 【同点優先】 case 診断結果 navigation | - | D=B同点 → D優先 | Answer the survey as following Q1 : B Q2 : D Q3 : D Q4 : B Q5 : D | Type D セルフ・ディスカバリー型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.2.2 |  | - | D=C同点 → D優先 | Answer the survey as following Q1 : D Q2 : C Q3 : D Q4 : C Q5 : C | Type D セルフ・ディスカバリー型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.2.3 |  | - | D=A同点 → D優先 | Answer the survey as following Q1 : D Q2 : A Q3 : A Q4 : A Q5 : A | Type D セルフ・ディスカバリー型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.2.4 |  | - | B=C同点 → B優先 | Answer the survey as following Q1 : D Q2 : C Q3 : B Q4 : C Q5 : B | Type B スマート・ステイ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.2.5 |  | - | A=B同点 → B優先 | Answer the survey as following Q1 : A Q2 : A Q3 : B Q4 : B Q5 : B | Type B スマート・ステイ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.2.6 |  | - | A=C同点 → C優先 | Answer the survey as following Q1 : C Q2 : A Q3 : A Q4 : C Q5 : C | Type C ディープ・ホスピタリティ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.2.7 |  | - | A=B=C=D同点 → D優先（最高優先） | Answer the survey as following Q1 : B Q2 : B Q3 : C Q4 : C Q5 : A | Type D セルフ・ディスカバリー型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.3.1 | 【Boundary values】 case 診断結果 navigation | - | B が C に 1点差で勝利 | Answer the survey as following Q1 : B Q2 : D Q3 : B Q4 : C Q5 : C | Type B スマート・ステイ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.3.2 |  | - | D が B に 1点差で勝利 | Answer the survey as following Q1 : D Q2 : B Q3 : D Q4 : B Q5 : D | Type D セルフ・ディスカバリー型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.3.3 |  | - | C の最高得点パターン（9点） | Answer the survey as following Q1 : C Q2 : C Q3 : C Q4 : B Q5 : C | Type C ディープ・ホスピタリティ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.4.1 | 【Distributed values】 pattern 診断結果 navigation | - | 交互回答 A→B→C→D→A パターン | Answer the survey as following Q1 : A Q2 : B Q3 : C Q4 : D Q5 : A | Type A イマーシブ・リラックス型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.5.1 | 【3方向同点】 pattern 診断結果 navigation | - | A=B=C同点 → B優先 | Answer the survey as following Q1 : A Q2 : A Q3 : B Q4 : C Q5 : B | Type B スマート・ステイ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.5.2 |  | - | A=C=D同点 → D優先 | Answer the survey as following Q1 : A Q2 : A Q3 : C Q4 : D Q5 : D | Type D セルフ・ディスカバリー型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.5.3 |  | - | A=B=D同点 → D優先 | Answer the survey as following Q1 : A Q2 : B Q3 : D Q4 : B Q5 : D | Type D セルフ・ディスカバリー型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.5.4 |  | - | B=C=D同点 → D優先 | Answer the survey as following Q1 : A Q2 : D Q3 : C Q4 : D Q5 : D | Type D セルフ・ディスカバリー型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.6.1 | 【全設問同一回答】 pattern 診断結果 navigation | - | 全設問A回答 → Aの最高得点（8点） | Answer the survey as following Q1 : A Q2 : A Q3 : A Q4 : A Q5 : A | Type A イマーシブ・リラックス型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.6.2 |  | - | 全設問B回答 → Bの最高得点（8点） | Answer the survey as following Q1 : B Q2 : B Q3 : B Q4 : B Q5 : B | Type B スマート・ステイ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
| 13.7.1 | 【Q4D異常系】 pattern 診断結果 navigation | - | Q4=D 選択時 → B に+1加算、D に+0（Q4Dの特殊スコア検証） | Answer the survey as following Q1 : A Q2 : A Q3 : D Q4 : D Q5 : B | Type B スマート・ステイ型 result screen |  | @Galyna Slobodyanyk |  | Pass | Pass
14 | 14.1 | 「診断結果をシェアする」 Share Survey results | User finished the survey | Verify sharing is possible through LINE | Tap [診断結果をシェアする] button Flex message is sent to selected friends | Friend will receive such type of message 【Hilton 理想のホテルステイ診断】 わたしは「〇〇型」でした。 |  | @Galyna Slobodyanyk |  | Pass | Pass
| 14.1.1 |  |  | Verify that user which received shared message has screen with 「自分でも診断してみる」(Try the diagnosis yourself) button | Tap on flex message | The screen with 「自分でも診断してみる」button opens |  | @Galyna Slobodyanyk |  | Pass | Pass
| 14.2 |  | User finished the survey | Verify sharing is possible through X | Tap [Xでシェアする] button | User can share results on X |  | @Galyna Slobodyanyk |  | Pass | Pass
Note on C5: [スレッド化されたコメント] 使用している Excel のバージョンでは、このスレッド化されたコメントを表示できますが、新しいバージョンの Excel でファイルを開いた場合はコメントに対する編集がすべて削除されます。詳細: https://go.microsoft.com/fwlink/?linkid=870924 コメント: Since this miniapp is an "always-on" event, as of now there is no event period set
Note on G33: [スレッド化されたコメント] 使用している Excel のバージョンでは、このスレッド化されたコメントを表示できますが、新しいバージョンの Excel でファイルを開いた場合はコメントに対する編集がすべて削除されます。詳細: https://go.microsoft.com/fwlink/?linkid=870924 コメント: Please use this sheet as reference as to which URL should be expected
Note on G41: [スレッド化されたコメント] 使用している Excel のバージョンでは、このスレッド化されたコメントを表示できますが、新しいバージョンの Excel でファイルを開いた場合はコメントに対する編集がすべて削除されます。詳細: https://go.microsoft.com/fwlink/?linkid=870924 コメント: We no longer included this push message in the requirements, so we can get rid of this point
Note on G43: [スレッド化されたコメント] 使用している Excel のバージョンでは、このスレッド化されたコメントを表示できますが、新しいバージョンの Excel でファイルを開いた場合はコメントに対する編集がすべて削除されます。詳細: https://go.microsoft.com/fwlink/?linkid=870924 コメント: Please use this sheet as reference as to which URL should be expected
Note on G51: [スレッド化されたコメント] 使用している Excel のバージョンでは、このスレッド化されたコメントを表示できますが、新しいバージョンの Excel でファイルを開いた場合はコメントに対する編集がすべて削除されます。詳細: https://go.microsoft.com/fwlink/?linkid=870924 コメント: We no longer included this push message in the requirements, so we can get rid of this point Reply... G43 ?? マスターデータで登録したおすすめのホテルステイのURLを開く
Note on G61: [スレッド化されたコメント] 使用している Excel のバージョンでは、このスレッド化されたコメントを表示できますが、新しいバージョンの Excel でファイルを開いた場合はコメントに対する編集がすべて削除されます。詳細: https://go.microsoft.com/fwlink/?linkid=870924 コメント: We no longer included this push message in the requirements, so we can get rid of this point Reply... G43 ?? マスターデータで登録したおすすめのホテルステイのURLを開く
Note on G71: [スレッド化されたコメント] 使用している Excel のバージョンでは、このスレッド化されたコメントを表示できますが、新しいバージョンの Excel でファイルを開いた場合はコメントに対する編集がすべて削除されます。詳細: https://go.microsoft.com/fwlink/?linkid=870924 コメント: We no longer included this push message in the requirements, so we can get rid of this point Reply... G43 ?? マスターデータで登録したおすすめのホテルステイのURLを開く
Note on G83: [スレッド化されたコメント] 使用している Excel のバージョンでは、このスレッド化されたコメントを表示できますが、新しいバージョンの Excel でファイルを開いた場合はコメントに対する編集がすべて削除されます。詳細: https://go.microsoft.com/fwlink/?linkid=870924 コメント: For users who have not completed the survey, they will start again at the LP

## Bug Report
Bug ID | Issue | Attachment #1 | Attachment #2 | Comments | Status | Priority | Issue Type
1 | on question 5 screen, after tapping each option, its image becomes highlighted in white and with gray brim |  |  | @Sun Moxi こちらも修正お願いいたします。 挙動は他の設問と同じように統一していただけますと幸いです。 - Daniel 4/2 2026/04/02 Tina Now gray brim is not displayed after selecting the option. Marking as 'Done' | Done | Medium | UI / UX
2 | question 2 screen: the options' font seems to be smaller than in reference |  |  |  | Reported
3 | After selection of the option it is not highlighted in white, except of questio 5 screen |  |  | @Sun Moxi こちら修正をお願いできますでしょうか？ - Daniel 04/02 @Daniel Magdi 2026/4/2 moxi 実装は完了しておりますが、Q1～Q4で白いハイライトが表示されない理由として、タップ後に即時で画面遷移が発生するためです。 一方で、Q5はローディング動画を表示する仕様のため、一定時間画面に留まる挙動となっています。 対応としてQ1～Q4でもハイライトを表示させることは可能ですが、その場合は画面遷移を遅らせる必要があり、ユーザー体験としてはテンポが悪くなる懸念があります。 現状の仕様のままで問題ないか、ご確認いただけますでしょうか。 @Sun Moxi 理解いたしました。ありがとうございました。 でしたら、現状の仕様のままで問題ございません！ 04/02 Daniel | Won't Fix | Medium | UI / UX
4 | Tapping the '診断タイプ一覧' button leads user to screen with types. The screen doesnt correspond to the design, horisontal scrolling is possible |  |  | 2024/04/02 Tina The screen is fixed. Marking as 'Done' | Done
5 | In Hilton flex message brackets 「 」are omitted. Should it be like that? |  |  | This is no problem! - Daniel 4/2 | Done
6 | On X when sharing a message, brackets 「 」are omitted. Should it be like that? |  |  | This is no problem! - Daniel 4/2 | Done
7 | The font of '詳細を見る' buttons should be displayed in bold (this applicable for each pattern) |  |  | 2026/04/06 Halya Buttons text is bold. Marking as Done | Done |  | UI / UX
8 | 診断結果画面 →「Xにシェア」のボタン内のテキストが左によっていた" |  |  | 2026/04/09 Daniel @Sun Moxiこちらご確認お願い致します。Figmaだと問題はなさそうです。 | Done | Medium | UI / UX
9 | ローディング画面の画像の解像度が低いように見える |  |  | 2026/04/09 Daniel @Sun Moxi確かにローディング画面のホテル写真の画像が粗いように見えるので、ご確認お願い致します。 | Done | Medium | UI / UX
10 | 診断結果ページが古いデザインになっています |  |  | 2026/04/09 Daniel @Sun Moxiすみません、診断結果画面と診断タイプ一覧を最新のものに差し替えをお願い致します。（テキストが一部変わっています - Dタイプが「アクティブ・ディスカバリー型」にタイトル変更） https://www.figma.com/design/yavHj44k0DMiQxzg5wo5HL/Hilton%E7%90%86%E6%83%B3%E3%81%AE%E3%83%9B%E3%83%86%E3%83%AB%E3%82%B9%E3%83%86%E3%82%A4%E8%A8%BA%E6%96%AD?node-id=382-777&t=54b4o4fGFsd2JJsD-0 | Done | High | UI / UX
11 | #10の変更に伴い、シェアメッセージのアップデートが必要 |  |  | 2026/04/09 Daniel @Sun Moxi診断結果タイプDのシェアメッセージを「アクティブ・ディスカバリー型」に画像とメッセージ内のテキストを変更お願い致します。 @Sun Moxi2026/04/13 こちらがまだ「セルフ・ディスカバリー型」のままの画像になっているので、ご確認お願い致します。（D列の画像参照） @Sun Moxi2026/04/23 こちらがまだ修正されていませんのでご確認お願い致します。 | Test | High | UI / UX
12 | インセンティブ付与の関係でLPのインセンティブ無しになったので、「答えてくれた人に特別なオファーも！」はトリでお願いいたします。 |  |  | 2026/04/09 Daniel @Aliciacc @Sun Moxi こちらLPのデザイン修正をお願い致します。（テキスト削除） | Done | High | UI / UX
13 | 診断結果ページシェアボタン修正 |  |  | 2026/04/09 Daniel @Aliciacc @Sun Moxi 今：診断結果をシェアする▶︎ 修正：LINEでシェアする▶︎ ※「診断結果をシェアする」だと、どこにシェアするかわからないため違和感があったため | Done | High | UI / UX
14 | Dのタイプ名アクティブ・ディスカバリー型のLIFF内に「おすすめホテル結果を確認する」のテキストが抜けています |  |  | 2026/04/13 @Sun Moxi こちら気付くのが遅くなり、すみません。 こちらテキスト抜けている部分ご確認いただけますでしょうか？ | Done | High | UI / UX
15 | LP画面：利用規約とプライバシーポリシー部分をタップすると遷移できない（前回のチェック時には遷移先できていた） |  |  | 04/23 Daniel @Sun MoxiLPでこちらのバグが起きているみたいです。（以前は大丈夫だったのですが）ご確認いただけますでしょうか？ | Test | High | Functionality
16 | LP画面：画面左下にローディング画面で掲示される画像が表示されている |  |  | 04/23 Daniel @Sun MoxiLPでこちらのバグが起きているみたいです。（以前は大丈夫だったのですが）ご確認いただけますでしょうか？ | Test | High | UI / UX,Functionality
17 | 診断結果画面（アクティブ・ディスカバリー型）のおすすめホテルの遷移先が異なる シート：https://docs.google.com/spreadsheets/d/1711wAs3bYVW_ThQzudSww5J4kZMkCGPbKKMpGDDvrRc/edit?gid=1556656707#gid=1556656707 （診断結果入稿シートシートのC列） |  |  | 04/23 Daniel @Sun Moxi こちら遷移先を再度ご確認いただけますと幸いです。 | Test | High | UI / UX,Functionality
18 | フォントが前回確認した内容（Figma上のデザイン）と異なる （前回確認した時は問題なかったです。） 今；Noto Sans JP 正：Figmaの内容 |  |  | 04/23 Daniel @Sun Moxi 前まで問題なかったのですが、今見るとフォントが変わっています。 | Test | High | UI / UX,Functionality
19 | シェアメッセージのイメージマップ画像が古いのが残ってます |  |  | 04/23 Daniel @Sun Moxi こちら最新に差し替えをお願いできますでしょうか？ (←Figmaのキャプチャ参考） 04/24 少文 @Daniel Magdicc @Sun Moxi 先にLINEのキャッシュを削除してから、もう一度お試しください。 | Test | High | UI / UX
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40